## Scope all
Sr. No. | Scope Items | Type | Scope Count | Initial Man Days | Received Count | Total Man Days | Web Application Completed | Completed VA count | Completed PT count | Methodology | Approach | Data Received | Actual initiation date | Actual end date | Remarks | Issues
1 | Web Applications | URL | 10 | 15 Days | 31 | 45 Days | 14 | N/A | N/A | VA+PT | Blackbox | 2025-05-16 | 2025-05-22 |  | #14 Web Applicaiton Initial Reports Submitted. #2 Internal Web Application reports under review. #2 Internal Web Applications testing in progress. | N/A
2 | Servers | IP | 300 | 40 Days | 342 | 46 Days | N/A | 295 | 89 | VA+PT | Blackbox | 2025-07-08 | 2025-07-09 |  | #15 Public Server IPs received. # 15 Public Server IPs Initial Report Submitted. #19 Internal Server IPs Initial Report Submitted. #327 Internal Server IPs received. #42 Excessive server IPs confirmation required. | IPs accessibility issue
3 | Network Devices | IP | 200 | 30 Days | 179 | 30 Days | N/A | 157 | 148 | VA+PT | Blackbox | 2025-07-09 | 2025-07-09 |  | #184 Network Device IPs received. #5 WLC IPs Batch Report submitted. #27 Switch IPs Batch Report submitted. #39 Access Point IPs Batch Report submitted. #22 Firewall IPs Batch Report submitted. #16 Network Devices IPs Yet To Receive. | IPs accessibility issue

## VAPT-Server
SR NO | Type | IP | VA Status | PT Status | Asignee | Batch | Remarks
1 | IDC Nated IP | 210.210.21.8 | Completed on 10-07-2025 | Completed on 11-07-2025 | Sukhada | External Server IPs Batch | Report Submitted on 25-07-2025
2 | IDC Nated IP | 210.210.21.9 | Completed on 10-07-2025 | Completed on 11-07-2025 | Sukhada | External Server IPs Batch | Report Submitted on 25-07-2025
3 | IDC Nated IP | 210.210.21.10 | Completed on 10-07-2025 | Completed on 11-07-2025 | Sukhada | External Server IPs Batch | Report Submitted on 25-07-2025
4 | IDC Nated IP | 210.210.21.24 | Completed on 10-07-2025 | Completed on 11-07-2025 | Sukhada | External Server IPs Batch | Report Submitted on 25-07-2025
5 | IDC Nated IP | 210.210.21.25 | Completed on 10-07-2025 | Completed on 11-07-2025 | Sukhada | External Server IPs Batch | Report Submitted on 25-07-2025
6 | IDC Nated IP | 210.210.21.30 | Completed on 10-07-2025 | Completed on 11-07-2025 | Sukhada | External Server IPs Batch | Report Submitted on 25-07-2025
7 | IDC Nated IP | 1.6.28.243 | Completed on 10-07-2025 | Completed on 11-07-2025 | Sukhada | External Server IPs Batch | Report Submitted on 25-07-2025
8 | IDC Nated IP | 1.6.30.198 | Completed on 10-07-2025 | Completed on 11-07-2025 | Sukhada | External Server IPs Batch | Report Submitted on 25-07-2025
9 | IDC Nated IP | 210.210.21.26 | Completed on 10-07-2025 | Completed on 11-07-2025 | Sukhada | External Server IPs Batch | Report Submitted on 25-07-2025
10 | IDC Nated IP | 210.210.21.15 | Completed on 10-07-2025 | Completed on 11-07-2025 | Sukhada | External Server IPs Batch | Report Submitted on 25-07-2025
11 | IDC Nated IP | 210.210.21.27 | Completed on 10-07-2025 | Completed on 11-07-2025 | Sukhada | External Server IPs Batch | Report Submitted on 25-07-2025
12 | IDC Nated IP | 1.6.20.196 | Completed on 10-07-2025 | Completed on 11-07-2025 | Sukhada | External Server IPs Batch | Report Submitted on 25-07-2025
13 | IDC Nated IP | 210.210.21.28 | Completed on 10-07-2025 | Completed on 11-07-2025 | Sukhada | External Server IPs Batch | Report Submitted on 25-07-2025
14 | IDC Nated IP | 210.210.21.29 | Completed on 10-07-2025 | Completed on 11-07-2025 | Sukhada | External Server IPs Batch | Report Submitted on 25-07-2025
15 | IDC Nated IP | 1.6.30.197 | Completed on 15-07-2025 | Completed on 16-07-2025 | Sukhada | External Server IPs Batch | Report Submitted on 25-07-2025
16 | Internal Server IP | 10.10.1.113 |  |  | Sukhada
17 | Internal Server IP | 10.10.1.117 |  |  | Sukhada
18 | Internal Server IP | 172.16.100.143 |  |  | Sukhada
19 | Internal Server IP | 172.18.81.2 |  |  | Sukhada
20 | Internal Server IP | 172.30.31.105 | Completed on 07-08-2025 | Completed on 11-08-2025 | Sukhada
21 | Internal Server IP | 172.30.31.106 | Completed on 07-08-2025 | Completed on 11-08-2025 | Sukhada
22 | Internal Server IP | 172.30.31.107 | Completed on 07-08-2025 | Completed on 12-08-2025 | Sukhada
23 | Internal Server IP | 172.30.35.61 | Completed on 07-08-2025 | Completed on 12-08-2025 | Sukhada
24 | Internal Server IP | 192.168.3.18 | Completed on 07-08-2025 | Completed on 18-09-2025 | Sukhada
25 | Internal Server IP | 192.168.3.20 | Completed on 07-08-2025 | Completed on 12-09-2025 | Sukhada
26 | Internal Server IP | 192.168.4.10 | Completed on 07-08-2025 | Completed on 12-09-2025 | Sukhada
27 | Internal Server IP | 192.168.4.18 | Completed on 07-08-2025 | Completed on 12-09-2025 | Sukhada
28 | Internal Server IP | 192.168.5.18 |  |  | Sukhada
29 | Internal Server IP | 192.168.5.20 |  |  | Sukhada
30 | Internal Server IP | 192.168.6.10 | Completed on 07-08-2025 | Completed on 12-09-2025 | Sukhada
31 | Internal Server IP | 192.168.6.14 | Completed on 07-08-2025 | Completed on 12-09-2025 | Sukhada
32 | Internal Server IP | 192.168.8.10 | Completed on 07-08-2025 | Completed on 18-09-2025 | Sukhada
33 | Internal Server IP | 192.168.8.12 | Completed on 07-08-2025 | Completed on 18-09-2025 | Sukhada
34 | Internal Server IP | 192.168.8.14 | Completed on 07-08-2025 | Completed on 18-09-2025 | Sukhada
35 | Internal Server IP | 192.168.8.17 | Completed on 07-08-2025 | Completed on 18-09-2025 | Sukhada
36 | Internal Server IP | 192.168.8.39 | Completed on 07-08-2025 | Completed on 19-09-2025 | Sukhada
37 | Internal Server IP | 192.168.8.78 | Completed on 07-08-2025 | Completed on 19-09-2025 | Sukhada
38 | Internal Server IP | 192.168.8.79 | Completed on 07-08-2025 | Completed on 19-09-2025 | Sukhada
39 | Internal Server IP | 192.168.8.102 | Completed on 07-08-2025 | Completed on 19-09-2025 | Sukhada
40 | Internal Server IP | 192.168.8.114 | Completed on 07-08-2025 | Completed on 19-09-2025 | Sukhada
41 | Internal Server IP | 192.168.10.2 | Completed on 07-08-2025 | Completed on 12-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
42 | Internal Server IP | 192.168.10.8 | Completed on 07-08-2025 | Completed on 13-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
43 | Internal Server IP | 192.168.10.11 | Completed on 07-08-2025 | Completed on 14-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
44 | Internal Server IP | 192.168.10.13 | Completed on 07-08-2025 | Completed on 14-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
45 | Internal Server IP | 192.168.10.14 | Completed on 07-08-2025 | Completed on 28-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
46 | Internal Server IP | 192.168.10.23 | Completed on 07-08-2025 | Completed on 13-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
47 | Internal Server IP | 192.168.10.30 | Completed on 07-08-2025 | Completed on 18-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
48 | Internal Server IP | 192.168.10.32 | Completed on 07-08-2025 | Completed on 19-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
49 | Internal Server IP | 192.168.10.34 |  |  | Sukhada
50 | Internal Server IP | 192.168.10.35 | Completed on 07-08-2025 | Completed on 19-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
51 | Internal Server IP | 192.168.10.36 |  |  | Sukhada
52 | Internal Server IP | 192.168.10.38 | Completed on 07-08-2025 |  | Sukhada
53 | Internal Server IP | 192.168.10.39 |  |  | Sukhada
54 | Internal Server IP | 192.168.10.42 | Completed on 07-08-2025 |  | Sukhada
55 | Internal Server IP | 192.168.10.45 | Completed on 07-08-2025 | Completed on 20-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
56 | Internal Server IP | 192.168.10.46 |  |  | Sukhada
57 | Internal Server IP | 192.168.10.47 | Completed on 07-08-2025 | Completed on 20-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
58 | Internal Server IP | 192.168.10.48 |  |  | Sukhada
59 | Internal Server IP | 192.168.10.49 |  |  | Sukhada
60 | Internal Server IP | 192.168.10.51 |  |  | Sukhada
61 | Internal Server IP | 192.168.10.55 |  |  | Sukhada
62 | Internal Server IP | 192.168.10.56 | Completed on 07-08-2025 | Completed on 20-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
63 | Internal Server IP | 192.168.10.57 | Completed on 07-08-2025 | Completed on 20-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
64 | Internal Server IP | 192.168.10.59 | Completed on 07-08-2025 | Completed on 20-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
65 | Internal Server IP | 192.168.10.62 |  |  | Sukhada
66 | Internal Server IP | 192.168.10.63 |  |  | Sukhada
67 | Internal Server IP | 192.168.10.71 | Completed on 07-08-2025 | Completed on 21-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
68 | Internal Server IP | 192.168.10.72 | Completed on 07-08-2025 | Completed on 21-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
69 | Internal Server IP | 192.168.10.73 | Completed on 07-08-2025 | Completed on 22-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
70 | Internal Server IP | 192.168.10.79 | Completed on 07-08-2025 | Completed on 22-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
71 | Internal Server IP | 192.168.10.82 | Completed on 07-08-2025 | Completed on 22-08-2025 | Sukhada | Internal Server IPs 192.168.10.x Subnet Batch-1 Report
72 | Internal Server IP | 192.168.10.83 |  |  | Sukhada
73 | Internal Server IP | 192.168.10.85 |  |  | Pratyaksha
74 | Internal Server IP | 192.168.10.86 |  |  | Pratyaksha
75 | Internal Server IP | 192.168.10.87 | Completed on 07-08-2025 |  | Pratyaksha
76 | Internal Server IP | 192.168.10.88 | Completed on 07-08-2025 |  | Pratyaksha
77 | Internal Server IP | 192.168.10.89 | Completed on 07-08-2025 |  | Pratyaksha
78 | Internal Server IP | 192.168.10.90 | Completed on 07-08-2025 |  | Pratyaksha
79 | Internal Server IP | 192.168.10.91 | Completed on 07-08-2025 |  | Pratyaksha
80 | Internal Server IP | 192.168.10.92 | Completed on 07-08-2025 |  | Pratyaksha
81 | Internal Server IP | 192.168.10.93 | Completed on 07-08-2025 |  | Pratyaksha
82 | Internal Server IP | 192.168.10.94 | Completed on 07-08-2025 |  | Pratyaksha
83 | Internal Server IP | 192.168.10.95 | Completed on 07-08-2025 |  | Pratyaksha
84 | Internal Server IP | 192.168.10.96 | Completed on 07-08-2025 |  | Pratyaksha
85 | Internal Server IP | 192.168.10.97 | Completed on 07-08-2025 |  | Pratyaksha
86 | Internal Server IP | 192.168.10.98 | Completed on 07-08-2025 |  | Pratyaksha
87 | Internal Server IP | 192.168.10.99 | Completed on 07-08-2025 |  | Pratyaksha
88 | Internal Server IP | 192.168.10.101 |  |  | Pratyaksha
89 | Internal Server IP | 192.168.10.103 | Completed on 07-08-2025 |  | Pratyaksha
90 | Internal Server IP | 192.168.10.104 | Completed on 07-08-2025 |  | Pratyaksha
91 | Internal Server IP | 192.168.10.105 | Completed on 07-08-2025 |  | Pratyaksha
92 | Internal Server IP | 192.168.10.107 | Completed on 07-08-2025 |  | Pratyaksha
93 | Internal Server IP | 192.168.10.109 | Completed on 07-08-2025 |  | Pratyaksha
94 | Internal Server IP | 192.168.10.110 | Completed on 07-08-2025 |  | Pratyaksha
95 | Internal Server IP | 192.168.10.111 | Completed on 07-08-2025 |  | Pratyaksha
96 | Internal Server IP | 192.168.10.112 | Completed on 07-08-2025 |  | Pratyaksha
97 | Internal Server IP | 192.168.10.113 | Completed on 07-08-2025 |  | Pratyaksha
98 | Internal Server IP | 192.168.10.114 | Completed on 07-08-2025 |  | Pratyaksha
99 | Internal Server IP | 192.168.10.115 | Completed on 07-08-2025 |  | Pratyaksha
100 | Internal Server IP | 192.168.10.116 | Completed on 07-08-2025 |  | Pratyaksha
101 | Internal Server IP | 192.168.10.119 | Completed on 07-08-2025 |  | Pratyaksha
102 | Internal Server IP | 192.168.10.120 | Completed on 07-08-2025 |  | Pratyaksha
103 | Internal Server IP | 192.168.10.121 | Completed on 07-08-2025 |  | Pratyaksha
104 | Internal Server IP | 192.168.10.122 | Completed on 07-08-2025 |  | Pratyaksha
105 | Internal Server IP | 192.168.10.124 |  |  | Sukhada
106 | Internal Server IP | 192.168.10.125 | Completed on 07-08-2025 | Completed on 29-08-2025 | Sukhada
107 | Internal Server IP | 192.168.10.127 | Completed on 07-08-2025 | Completed on 29-08-2025 | Sukhada
108 | Internal Server IP | 192.168.10.130 | Completed on 07-08-2025 | Completed on 01-09-2025 | Sukhada
109 | Internal Server IP | 192.168.10.132 | Completed on 07-08-2025 | Completed on 01-09-2025 | Sukhada
110 | Internal Server IP | 192.168.10.134 | Completed on 07-08-2025 | Completed on 01-09-2025 | Sukhada
111 | Internal Server IP | 192.168.10.135 | Completed on 07-08-2025 | Completed on 01-09-2025 | Sukhada
112 | Internal Server IP | 192.168.10.136 | Completed on 07-08-2025 | Completed on 02-09-2025 | Sukhada
113 | Internal Server IP | 192.168.10.141 | Completed on 07-08-2025 | Completed on 04-09-2025 | Sukhada
114 | Internal Server IP | 192.168.10.142 | Completed on 07-08-2025 | Completed on 02-09-2025 | Sukhada
115 | Internal Server IP | 192.168.10.144 | Completed on 07-08-2025 | Completed on 02-09-2025 | Sukhada
116 | Internal Server IP | 192.168.10.145 | Completed on 07-08-2025 | Completed on 02-09-2025 | Sukhada
117 | Internal Server IP | 192.168.10.148 | Completed on 07-08-2025 | Completed on 02-09-2025 | Sukhada
118 | Internal Server IP | 192.168.10.149 | Completed on 07-08-2025 | Completed on 03-09-2025 | Sukhada
119 | Internal Server IP | 192.168.10.150 | Completed on 07-08-2025 | Completed on 03-09-2025 | Sukhada
120 | Internal Server IP | 192.168.10.151 | Completed on 07-08-2025 | Completed on 03-09-2025 | Sukhada
121 | Internal Server IP | 192.168.10.152 | Completed on 07-08-2025 | Completed on 04-09-2025 | Sukhada
122 | Internal Server IP | 192.168.10.153 | Completed on 07-08-2025 | Completed on 04-09-2025 | Sukhada
123 | Internal Server IP | 192.168.10.154 |  |  | Sukhada
124 | Internal Server IP | 192.168.10.155 | Completed on 07-08-2025 | Completed on 06-09-2025 | Sukhada
125 | Internal Server IP | 192.168.10.156 | Completed on 07-08-2025 | Completed on 06-09-2025 | Sukhada
126 | Internal Server IP | 192.168.10.157 | Completed on 07-08-2025 | Completed on 08-09-2025 | Sukhada
127 | Internal Server IP | 192.168.10.158 | Completed on 07-08-2025 | Completed on 08-09-2025 | Sukhada
128 | Internal Server IP | 192.168.10.161 | Completed on 07-08-2025 | Completed on 09-09-2025 | Sukhada
129 | Internal Server IP | 192.168.10.162 | Completed on 07-08-2025 | Completed on 09-09-2025 | Sukhada
130 | Internal Server IP | 192.168.10.163 | Completed on 07-08-2025 | Completed on 09-09-2025 | Sukhada
131 | Internal Server IP | 192.168.10.165 | Completed on 07-08-2025 | Completed on 10-09-2025 | Sukhada
132 | Internal Server IP | 192.168.10.166 | Completed on 07-08-2025 | Completed on 10-09-2025 | Sukhada
133 | Internal Server IP | 192.168.10.168 |  |  | Sukhada
134 | Internal Server IP | 192.168.10.169 | Completed on 07-08-2025 | Completed on 11-09-2025 | Sukhada
135 | Internal Server IP | 192.168.10.170 | Completed on 07-08-2025 | Completed on 11-09-2025 | Sukhada
136 | Internal Server IP | 192.168.10.172 | Completed on 07-08-2025 | Completed on 11-09-2025 | Sukhada
137 | Internal Server IP | 192.168.10.173 | Completed on 07-08-2025 |  | Pratyaksha
138 | Internal Server IP | 192.168.10.174 | Completed on 07-08-2025 |  | Pratyaksha
139 | Internal Server IP | 192.168.10.175 | Completed on 07-08-2025 |  | Pratyaksha
140 | Internal Server IP | 192.168.10.177 |  |  | Pratyaksha
141 | Internal Server IP | 192.168.10.182 | Completed on 07-08-2025 |  | Pratyaksha
142 | Internal Server IP | 192.168.10.184 | Completed on 07-08-2025 |  | Pratyaksha
143 | Internal Server IP | 192.168.10.190 |  |  | Pratyaksha
144 | Internal Server IP | 192.168.10.192 | Completed on 07-08-2025 |  | Pratyaksha
145 | Internal Server IP | 192.168.10.193 | Completed on 07-08-2025 |  | Pratyaksha
146 | Internal Server IP | 192.168.10.194 | Completed on 07-08-2025 |  | Pratyaksha
147 | Internal Server IP | 192.168.10.197 | Completed on 07-08-2025 |  | Pratyaksha
148 | Internal Server IP | 192.168.10.201 | Completed on 07-08-2025 |  | Pratyaksha
149 | Internal Server IP | 192.168.10.204 | Completed on 07-08-2025 |  | Pratyaksha
150 | Internal Server IP | 192.168.10.206 | Completed on 07-08-2025 |  | Pratyaksha
151 | Internal Server IP | 192.168.10.207 | Completed on 07-08-2025 |  | Pratyaksha
152 | Internal Server IP | 192.168.10.209 | Completed on 07-08-2025 |  | Pratyaksha
153 | Internal Server IP | 192.168.10.210 | Completed on 07-08-2025 |  | Pratyaksha
154 | Internal Server IP | 192.168.10.211 | Completed on 07-08-2025 |  | Pratyaksha
155 | Internal Server IP | 192.168.10.213 | Completed on 07-08-2025 |  | Pratyaksha
156 | Internal Server IP | 192.168.10.217 | Completed on 07-08-2025 |  | Pratyaksha
157 | Internal Server IP | 192.168.10.218 | Completed on 07-08-2025 |  | Pratyaksha
158 | Internal Server IP | 192.168.10.220 |  |  | Pratyaksha
159 | Internal Server IP | 192.168.10.230 | Completed on 07-08-2025 |  | Pratyaksha
160 | Internal Server IP | 192.168.10.231 | Completed on 07-08-2025 |  | Pratyaksha
161 | Internal Server IP | 192.168.10.232 | Completed on 07-08-2025 |  | Pratyaksha
162 | Internal Server IP | 192.168.10.233 | Completed on 07-08-2025 |  | Pratyaksha
163 | Internal Server IP | 192.168.10.234 | Completed on 07-08-2025 |  | Pratyaksha
164 | Internal Server IP | 192.168.10.235 | Completed on 07-08-2025 |  | Pratyaksha
165 | Internal Server IP | 192.168.10.236 | Completed on 07-08-2025 |  | Pratyaksha
166 | Internal Server IP | 192.168.10.237 | Completed on 07-08-2025 |  | Pratyaksha
167 | Internal Server IP | 192.168.10.254 |  |  | Pratyaksha
168 | Internal Server IP | 192.168.11.1 | Completed on 07-08-2025 |  | Pratyaksha
169 | Internal Server IP | 192.168.11.2 | Completed on 07-08-2025 |  | Pratyaksha
170 | Internal Server IP | 192.168.11.9 | Completed on 07-08-2025 |  | Pratyaksha
171 | Internal Server IP | 192.168.11.25 | Completed on 07-08-2025 |  | Pratyaksha
172 | Internal Server IP | 192.168.11.29 | Completed on 07-08-2025 |  | Pratyaksha
173 | Internal Server IP | 192.168.11.34 |  |  | Pratyaksha
174 | Internal Server IP | 192.168.11.35 | Completed on 07-08-2025 |  | Pratyaksha
175 | Internal Server IP | 192.168.11.36 | Completed on 07-08-2025 |  | Pratyaksha
176 | Internal Server IP | 192.168.11.37 | Completed on 07-08-2025 |  | Pratyaksha
177 | Internal Server IP | 192.168.11.38 | Completed on 07-08-2025 |  | Pratyaksha
178 | Internal Server IP | 192.168.11.43 | Completed on 07-08-2025 |  | Pratyaksha
179 | Internal Server IP | 192.168.11.45 | Completed on 07-08-2025 |  | Pratyaksha
180 | Internal Server IP | 192.168.11.46 | Completed on 07-08-2025 |  | Pratyaksha
181 | Internal Server IP | 192.168.11.51 | Completed on 07-08-2025 |  | Pratyaksha
182 | Internal Server IP | 192.168.11.52 | Completed on 07-08-2025 |  | Pratyaksha
183 | Internal Server IP | 192.168.11.53 | Completed on 07-08-2025 |  | Pratyaksha
184 | Internal Server IP | 192.168.11.58 | Completed on 07-08-2025 |  | Pratyaksha
185 | Internal Server IP | 192.168.11.63 | Completed on 07-08-2025 |  | Pratyaksha
186 | Internal Server IP | 192.168.11.78 | Completed on 07-08-2025 |  | Pratyaksha
187 | Internal Server IP | 192.168.11.79 | Completed on 07-08-2025 |  | Pratyaksha
188 | Internal Server IP | 192.168.11.81 | Completed on 07-08-2025 |  | Pratyaksha
189 | Internal Server IP | 192.168.11.87 | Completed on 07-08-2025 |  | Pratyaksha
190 | Internal Server IP | 192.168.11.88 | Completed on 07-08-2025 |  | Pratyaksha
191 | Internal Server IP | 192.168.11.90 | Completed on 07-08-2025 |  | Pratyaksha
192 | Internal Server IP | 192.168.11.93 | Completed on 07-08-2025 |  | Pratyaksha
193 | Internal Server IP | 192.168.11.95 | Completed on 07-08-2025 |  | Pratyaksha
194 | Internal Server IP | 192.168.11.97 | Completed on 07-08-2025 |  | Pratyaksha
195 | Internal Server IP | 192.168.11.99 | Completed on 07-08-2025 |  | Pratyaksha
196 | Internal Server IP | 192.168.11.100 | Completed on 07-08-2025 |  | Pratyaksha
197 | Internal Server IP | 192.168.11.103 | Completed on 07-08-2025 | Completed on 24-09-2025 | Deepak
198 | Internal Server IP | 192.168.11.104 | Completed on 07-08-2025 | Completed on 24-09-2025 | Deepak
199 | Internal Server IP | 192.168.11.107 | Completed on 07-08-2025 | Completed on 24-09-2025 | Deepak
200 | Internal Server IP | 192.168.11.108 | Completed on 07-08-2025 | Completed on 24-09-2025 | Deepak
201 | Internal Server IP | 192.168.11.109 | Completed on 07-08-2025 | Completed on 24-09-2025 | Deepak
202 | Internal Server IP | 192.168.11.110 |  | Completed on 24-09-2025 | Deepak
203 | Internal Server IP | 192.168.11.111 | Completed on 07-08-2025 | Completed on 25-09-2030 | Deepak
204 | Internal Server IP | 192.168.11.113 | Completed on 07-08-2025 |  | Deepak
205 | Internal Server IP | 192.168.11.114 | Completed on 07-08-2025 |  | Deepak
206 | Internal Server IP | 192.168.11.115 | Completed on 07-08-2025 |  | Deepak
207 | Internal Server IP | 192.168.11.116 | Completed on 07-08-2025 |  | Deepak
208 | Internal Server IP | 192.168.11.119 | Completed on 07-08-2025 |  | Deepak
209 | Internal Server IP | 192.168.11.122 | Completed on 07-08-2025 |  | Deepak
210 | Internal Server IP | 192.168.11.175 | Completed on 07-08-2025 |  | Deepak
211 | Internal Server IP | 192.168.11.179 | Completed on 07-08-2025 |  | Deepak
212 | Internal Server IP | 192.168.11.185 | Completed on 07-08-2025 |  | Deepak
213 | Internal Server IP | 192.168.11.186 | Completed on 07-08-2025 |  | Deepak
214 | Internal Server IP | 192.168.11.187 | Completed on 07-08-2025 |  | Deepak
215 | Internal Server IP | 192.168.11.188 | Completed on 07-08-2025 |  | Deepak
216 | Internal Server IP | 192.168.11.189 |  |  | Deepak
217 | Internal Server IP | 192.168.11.191 | Completed on 07-08-2025 |  | Deepak
218 | Internal Server IP | 192.168.11.192 | Completed on 07-08-2025 |  | Deepak
219 | Internal Server IP | 192.168.11.194 | Completed on 07-08-2025 |  | Deepak
220 | Internal Server IP | 192.168.11.197 | Completed on 07-08-2025 |  | Deepak
221 | Internal Server IP | 192.168.11.199 | Completed on 07-08-2025 |  | Deepak
222 | Internal Server IP | 192.168.11.201 | Completed on 07-08-2025 |  | Deepak
223 | Internal Server IP | 192.168.11.226 | Completed on 07-08-2025 |  | Deepak
224 | Internal Server IP | 192.168.11.233 | Completed on 07-08-2025 |  | Deepak
225 | Internal Server IP | 192.168.11.250 |  |  | Deepak
226 | Internal Server IP | 192.168.15.15 | Completed on 07-08-2025 |  | Deepak
227 | Internal Server IP | 192.168.15.18 | Completed on 07-08-2025 |  | Deepak
228 | Internal Server IP | 192.168.15.24 | Completed on 07-08-2025 |  | Deepak
229 | Internal Server IP | 192.168.15.25 | Completed on 07-08-2025 |  | Deepak
230 | Internal Server IP | 192.168.15.62 | Completed on 07-08-2025 |  | Deepak
231 | Internal Server IP | 192.168.25.10 | Completed on 07-08-2025 |  | Deepak
232 | Internal Server IP | 192.168.25.12 | Completed on 07-08-2025 |  | Deepak
233 | Internal Server IP | 192.168.25.209 | Completed on 07-08-2025 |  | Deepak
234 | Internal Server IP | 192.168.41.30 | Completed on 07-08-2025 |  | Deepak
235 | Internal Server IP | 192.168.41.40 | Completed on 07-08-2025 |  | Deepak
236 | Internal Server IP | 192.168.41.143 | Completed on 07-08-2025 |  | Deepak
237 | Internal Server IP | 192.168.41.250 | Completed on 07-08-2025 |  | Deepak
238 | Internal Server IP | 192.168.51.20 | Completed on 07-08-2025 |  | Deepak
239 | Internal Server IP | 192.168.51.201 | Completed on 07-08-2025 |  | Deepak
240 | Internal Server IP | 192.168.51.220 | Completed on 07-08-2025 |  | Deepak
241 | Internal Server IP | 192.168.51.224 | Completed on 07-08-2025 |  | Deepak
242 | Internal Server IP | 192.168.56.2 | Completed on 07-08-2025 |  | Deepak
243 | Internal Server IP | 192.168.56.15 | Completed on 07-08-2025 |  | Deepak
244 | Internal Server IP | 192.168.56.18 | Completed on 07-08-2025 |  | Deepak
245 | Internal Server IP | 192.168.56.25 | Completed on 07-08-2025 |  | Deepak
246 | Internal Server IP | 192.168.56.36 | Completed on 07-08-2025 |  | Deepak
247 | Internal Server IP | 192.168.56.37 | Completed on 07-08-2025 |  | Deepak
248 | Internal Server IP | 192.168.70.1 |  |  | Pratyaksha
249 | Internal Server IP | 192.168.70.14 | Completed on 07-08-2025 |  | Pratyaksha
250 | Internal Server IP | 192.168.70.16 | Completed on 07-08-2025 |  | Pratyaksha
251 | Internal Server IP | 192.168.70.17 | Completed on 07-08-2025 |  | Pratyaksha
252 | Internal Server IP | 192.168.70.18 | Completed on 07-08-2025 |  | Pratyaksha
253 | Internal Server IP | 192.168.70.19 | Completed on 07-08-2025 |  | Pratyaksha
254 | Internal Server IP | 192.168.70.20 | Completed on 07-08-2025 |  | Pratyaksha
255 | Internal Server IP | 192.168.70.21 | Completed on 07-08-2025 |  | Pratyaksha
256 | Internal Server IP | 192.168.70.22 | Completed on 07-08-2025 |  | Pratyaksha
257 | Internal Server IP | 192.168.70.24 | Completed on 07-08-2025 |  | Pratyaksha
258 | Internal Server IP | 192.168.70.39 | Completed on 07-08-2025 |  | Pratyaksha
259 | Internal Server IP | 192.168.70.43 | Completed on 07-08-2025 |  | Pratyaksha
260 | Internal Server IP | 192.168.70.44 | Completed on 07-08-2025 |  | Pratyaksha
261 | Internal Server IP | 192.168.70.45 | Completed on 07-08-2025 |  | Pratyaksha
262 | Internal Server IP | 192.168.70.46 |  |  | Pratyaksha
263 | Internal Server IP | 192.168.70.47 | Completed on 07-08-2025 |  | Pratyaksha
264 | Internal Server IP | 192.168.70.51 | Completed on 07-08-2025 |  | Pratyaksha
265 | Internal Server IP | 192.168.70.52 | Completed on 07-08-2025 |  | Pratyaksha
266 | Internal Server IP | 192.168.70.53 | Completed on 07-08-2025 |  | Pratyaksha
267 | Internal Server IP | 192.168.70.54 | Completed on 07-08-2025 |  | Pratyaksha
268 | Internal Server IP | 192.168.70.55 |  |  | Pratyaksha
269 | Internal Server IP | 192.168.70.56 |  |  | Pratyaksha
270 | Internal Server IP | 192.168.70.57 |  |  | Pratyaksha
271 | Internal Server IP | 192.168.70.58 | Completed on 07-08-2025 |  | Pratyaksha
272 | Internal Server IP | 192.168.70.59 | Completed on 07-08-2025 |  | Pratyaksha
273 | Internal Server IP | 192.168.70.60 | Completed on 07-08-2025 |  | Pratyaksha
274 | Internal Server IP | 192.168.70.61 |  |  | Pratyaksha
275 | Internal Server IP | 192.168.71.6 | Completed on 07-08-2025 |  | Deepak
276 | Internal Server IP | 192.168.71.22 | Completed on 07-08-2025 |  | Deepak
277 | Internal Server IP | 192.168.71.150 | Completed on 07-08-2025 |  | Deepak
278 | Internal Server IP | 192.168.71.175 | Completed on 07-08-2025 |  | Deepak
279 | Internal Server IP | 192.168.71.245 | Completed on 07-08-2025 |  | Deepak
280 | Internal Server IP | 192.168.81.3 | Completed on 07-08-2025 |  | Pratyaksha
281 | Internal Server IP | 192.168.81.5 | Completed on 07-08-2025 |  | Pratyaksha
282 | Internal Server IP | 192.168.81.6 |  |  | Pratyaksha
283 | Internal Server IP | 192.168.81.89 | Completed on 07-08-2025 |  | Pratyaksha
284 | Internal Server IP | 192.168.81.96 | Completed on 07-08-2025 |  | Pratyaksha
285 | Internal Server IP | 192.168.81.97 | Completed on 07-08-2025 |  | Pratyaksha
286 | Internal Server IP | 192.168.81.101 | Completed on 07-08-2025 |  | Pratyaksha
287 | Internal Server IP | 192.168.81.102 | Completed on 07-08-2025 |  | Pratyaksha
288 | Internal Server IP | 192.168.84.2 |  |  | Deepak
289 | Internal Server IP | 192.168.84.3 |  |  | Deepak
290 | Internal Server IP | 192.168.84.11 | Completed on 07-08-2025 |  | Deepak
291 | Internal Server IP | 192.168.84.17 | Completed on 07-08-2025 |  | Deepak
292 | Internal Server IP | 192.168.84.67 |  |  | Deepak
293 | Internal Server IP | 192.168.95.8 | Completed on 07-08-2025 |  | Pratyaksha
294 | Internal Server IP | 192.168.95.37 |  |  | Pratyaksha
295 | Internal Server IP | 192.168.95.38 |  |  | Pratyaksha
296 | Internal Server IP | 192.168.95.140 | Completed on 07-08-2025 |  | Pratyaksha
297 | Internal Server IP | 192.168.95.141 | Completed on 07-08-2025 |  | Pratyaksha
298 | Internal Server IP | 192.168.95.162 | Completed on 07-08-2025 |  | Pratyaksha
299 | Internal Server IP | 192.168.95.230 | Completed on 07-08-2025 |  | Pratyaksha
300 | Internal Server IP | 192.168.95.233 | Completed on 07-08-2025 |  | Pratyaksha
301 | Internal Server IP | 192.168.95.244 | Completed on 07-08-2025 |  | Pratyaksha
302 | Internal Server IP | 192.168.95.245 | Completed on 07-08-2025 |  | Pratyaksha
303 | Internal Server IP | 192.168.100.12 |  |  | Pratyaksha
304 | Internal Server IP | 192.168.100.42 | Completed on 07-08-2025 |  | Pratyaksha
305 | Internal Server IP | 192.168.100.46 | Completed on 07-08-2025 |  | Pratyaksha
306 | Internal Server IP | 192.168.100.48 | Completed on 07-08-2025 |  | Pratyaksha
307 | Internal Server IP | 192.168.100.65 | Completed on 07-08-2025 |  | Pratyaksha
308 | Internal Server IP | 192.168.100.78 | Completed on 07-08-2025 |  | Pratyaksha
309 | Internal Server IP | 192.168.100.79 | Completed on 07-08-2025 |  | Pratyaksha
310 | Internal Server IP | 192.168.100.152 | Completed on 07-08-2025 |  | Pratyaksha
311 | Internal Server IP | 192.168.100.155 | Completed on 07-08-2025 |  | Pratyaksha
312 | Internal Server IP | 192.168.100.208 | Completed on 07-08-2025 |  | Pratyaksha
313 | Internal Server IP | 192.168.101.17 |  |  | Deepak
314 | Internal Server IP | 192.168.101.18 | Completed on 07-08-2025 |  | Deepak
315 | Internal Server IP | 192.168.101.39 | Completed on 07-08-2025 |  | Deepak
316 | Internal Server IP | 192.168.101.43 | Completed on 07-08-2025 |  | Deepak
317 | Internal Server IP | 192.168.101.44 | Completed on 07-08-2025 |  | Deepak
318 | Internal Server IP | 192.168.101.139 | Completed on 07-08-2025 |  | Deepak
319 | Internal Server IP | 192.168.105.35 | Completed on 07-08-2025 |  | Deepak
320 | Internal Server IP | 192.168.105.36 | Completed on 07-08-2025 |  | Deepak
321 | Internal Server IP | 192.168.105.37 | Completed on 07-08-2025 |  | Deepak
322 | Internal Server IP | 192.168.105.38 | Completed on 07-08-2025 |  | Deepak
323 | Internal Server IP | 192.168.121.4 | Completed on 07-08-2025 |  | Deepak
324 | Internal Server IP | 192.168.121.5 | Completed on 07-08-2025 |  | Deepak
325 | Internal Server IP | 192.168.121.31 | Completed on 07-08-2025 |  | Deepak
326 | Internal Server IP | 192.168.121.66 | Completed on 07-08-2025 |  | Deepak
327 | Internal Server IP | 192.168.124.30 | Completed on 07-08-2025 |  | Pratyaksha
328 | Internal Server IP | 192.168.124.31 | Completed on 07-08-2025 |  | Pratyaksha
329 | Internal Server IP | 192.168.124.32 | Completed on 07-08-2025 |  | Pratyaksha
330 | Internal Server IP | 192.168.124.33 | Completed on 07-08-2025 |  | Pratyaksha
331 | Internal Server IP | 192.168.124.34 |  |  | Pratyaksha
332 | Internal Server IP | 192.168.124.35 | Completed on 07-08-2025 |  | Pratyaksha
333 | Internal Server IP | 192.168.124.38 | Completed on 07-08-2025 |  | Pratyaksha
334 | Internal Server IP | 192.168.124.41 | Completed on 07-08-2025 |  | Pratyaksha
335 | Internal Server IP | 192.168.124.44 | Completed on 07-08-2025 |  | Pratyaksha
336 | Internal Server IP | 192.168.145.36 | Completed on 07-08-2025 |  | Pratyaksha
337 | Internal Server IP | 192.168.145.37 | Completed on 07-08-2025 |  | Pratyaksha
338 | Internal Server IP | 192.168.145.38 | Completed on 07-08-2025 |  | Pratyaksha
339 | Internal Server IP | 192.168.145.39 | Completed on 07-08-2025 |  | Pratyaksha
340 | Internal Server IP | 192.168.145.40 | Completed on 07-08-2025 |  | Pratyaksha
341 | Internal Server IP | 192.168.145.47 | Completed on 07-08-2025 |  | Pratyaksha
342 | Internal Server IP | 192.168.145.48 | Completed on 07-08-2025 |  | Pratyaksha

## VAPT- Web-Application
Sr No | Application Name | Web URL | Interface | Execution | Assignee | Start Date | End Date | Report Release Date | Remarks
1 | Epl global | https://www.eplglobal.com/ | External | Black Box | Pratyaksha | 2025-05-22 | 2025-05-30 | 2025-05-30 | #Initial Scan Report sent
2 | Cognos | http://192.168.10.141:9510/tm1web/ | Internal | Black Box | Sukhada | 2025-05-22 | 2025-05-30 | 2025-05-30 | #Initial Scan Report sent
3 | E-Act | https://e-act.eplglobal.com/WebCenter_Inst/login.jsp | External | Black Box | Sukhada | 2025-05-28 | 2025-06-05 | 2025-06-05 | #Initial Scan Report sent
4 | Eprism | https://performancemanager5.successfactors.eu/login?company=esselpropaP&loginMethod=PWD#/login | External | Black Box | Pratyaksha | 2025-06-03 | 2025-10-06 | 2025-10-06 | #Initial Scan Report sent
5 | Entgra | https://entgra.eplglobal.com/bpmn | Internal | Black Box | Sukhada | 2025-06-11 | 2025-06-25 | 2025-06-25 | #Initial Scan Report sent
6 | Safety portal | https://entgra.eplglobal.com/bpmn | Internal | Black Box |  |  |  |  | Application is excluded as confirmed by Jitendra.As this is the Duplicate URL of Entgra.
7 | Zing Hr | https://portal.zinghr.com/2015/pages/authentication/zing.aspx?ccode=essel | External | Black Box | Pratyaksha | 2025-06-12 | 2025-06-23 | 2025-06-23 | #Initial Scan Report sent
8 | Epl Dashboard | https://app.powerbi.com/singleSignOn?ru=https%3A%2F%2Fapp.powerbi.com%2Fgroups%2F82d3ef2d-811b-4fee-a6ef-c624a832a66f%2Flist%3FnoSignUpCheck%3D1 | External | Black Box |  |  |  |  | Application is excluded as confirmed by Jitendra. As this is the PowerBi Application.
9 | SAP Authorization System | http://epconnectn:8095/ | Internal | Black Box | Pratyaksha | 2025-06-26 | 2025-07-03 | 2025-07-03 | #Initial Scan Report sent
10 | LabourWorks | https://eplclms.eplglobal.com/labourworks/login.aspx | External | Black Box | Sukhada | 2025-06-24 | 2025-07-01 | 2025-07-01 | #Initial Scan Report sent #Rescan received on 1-09-2025 #Draft rescan report sent on 04-09-2025
11 | BPM | https://bpm.eplglobal.com/EVIM | External | Black Box | Sukhada | 2025-07-01 | 2025-07-03 | 2025-07-03 | #Initial Scan Report sent
12 | ESOP | https://esop.eplglobal.com/ | Internal | Black Box | Pratyaksha | 2025-07-03 | 2025-07-05 | 2025-07-05 | #Initial Scan Report sent
13 | ITSM | https://digitaldesk.eplglobal.com/digitaldesk/ | External | Black Box | Om | 2025-08-13 | 2025-08-14 | 2025-09-02 | #Initial Scan Report sent
14 | Legatrix | https://legatrix.eplglobal.com/ | Internal | Black Box | Sukhada | 2025-09-22 | 2025-09-24 |  | #Report under review
15 | Insilysis | http://192.168.10.201:81/Login1.aspx | Internal | Black Box | Sukhada | 2025-09-25 |  |  | #Testing in progress
16 | Digital Port Folio | https://e-tubes.eplglobal.com:4433/epl/ | Internal | Black Box | Sukhada |  |  |  | #To be initiated
17 | EndPointCentral | https://endpointcentral.eplglobal.com:8383/client#/login | External | Black Box | Sayali | 2025-09-04 | 2025-09-08 | 2025-09-15 | #Initial Scan Report sent
18 | AD 360 | https://ad360.eplglobal.com:8445/AppsHome.do | Internal | Black Box | Sayali | 2025-09-22 | 2025-09-24 |  | #Report under review
19 | AD Audit | https://adaudit.eplglobal.com:8444/ | Internal | Black Box | Sukhada |  |  |  | #To be initiated
20 | AD Manager | http://admanager.eplglobal.com | Internal | Black Box | Sayali |  |  |  | #To be initiated
21 | eAudit | https://eaudit.eplglobal.com/ | Internal | Black Box | Sukhada |  |  |  | #To be initiated
22 | EPInsight QA Module | http://192.168.10.142:5050/main.html | Internal | Black Box | Sayali | 2025-09-25 |  |  | #Testing in progress
23 | Quality Module | http://192.168.10.142:8000/main | Internal | Black Box | Sayali |  |  |  | #To be initiated
24 | OneEPL Prod | https://oneepl.eplglobal.com:9097/OneEPL | Internal | Black Box |  |  |  |  | #Redirected to Microsoft Login Page
25 | FIORI | https://vdmapp.esselpropack.com:44301/sap/bc/ui5_ui5/ui2/ushell/shells/abap/FioriLaunchpad.html#Shell-home | External | Black Box | Om | 2025-09-04 | 2025-09-08 | 2025-09-10 | #Initial Scan Report sent
26 | AWO | https://oneepl.eplglobal.com:9092/ | Internal | Black Box |  |  |  |  | #Redirected to Microsoft Login Page
27 | Capex | https://oneepl.eplglobal.com:9096/Pages/DashboardPage.aspx | Internal | Black Box |  |  |  |  | #Redirected to Microsoft Login Page
28 | SAP Access Management | https://oneepl.eplglobal.com:9094/ | Internal | Black Box |  |  |  |  | #Redirected to Microsoft Login Page
29 | Asset Transfer System | https://oneepl.eplglobal.com:9091/ | Internal | Black Box |  |  |  |  | #Redirected to Microsoft Login Page
30 | DWO | https://oneepl.eplglobal.com:9095/ | Internal | Black Box |  |  |  |  | #Redirected to Microsoft Login Page
31 | IWO | https://oneepl.eplglobal.com:9093/ | Internal | Black Box |  |  |  |  | #Redirected to Microsoft Login Page
32 | Employee Reimbursement | https://epl.smartdocscloud.com/#/sp/auth/login | External | Black Box | Sayali | 2025-09-10 | 2025-09-14 | 2025-09-15 | #Initial Scan Report sent
33 | iRaje | iraje.eplglobal.com | Internal | Black Box | Sayali |  |  |  | #To be initiated

## VAPT-Network devices
SR NO | TYPE | IP ADDRESS | VA Status | PT Status | Assigned | Batch | Remarks
1 | Firewall | 5.5.5.1 | Completed on 11-07-2025 | Completed on 22-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
2 | Firewall | 172.30.30.4 | Completed on 11-07-2025 | Completed on 22-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
3 | Firewall | 192.168.3.1 | Completed on 11-07-2025 | Completed on 22-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
4 | Firewall | 192.168.4.1 | Completed on 11-07-2025 | Completed on 22-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
5 | Firewall | 192.168.6.12 | Completed on 11-07-2025 | Completed on 22-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
6 | Firewall | 192.168.8.1 | Completed on 11-07-2025 | Completed on 22-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
7 | Firewall | 192.168.11.105 | Completed on 11-07-2025 | Completed on 22-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
8 | Firewall | 192.168.15.19 | Completed on 11-07-2025 | Completed on 16-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
9 | Firewall | 192.168.25.3 | Completed on 11-07-2025 | Completed on 16-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
10 | Firewall | 192.168.30.1 |  |  | Pratyaksha | Internal Firewall IPs Batch | On hold due to Accessibility Issue
11 | Firewall | 192.168.41.7 | Completed on 11-07-2025 | Completed on 23-07-2025 | Sukhada | Internal Firewall IPs Batch | Report submitted on 04-09-2025
12 | Firewall | 192.168.51.24 | Completed on 11-07-2025 | Completed on 23-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
13 | Firewall | 192.168.56.7 | Completed on 11-07-2025 | Completed on 23-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
14 | Firewall | 192.168.71.8 | Completed on 11-07-2025 | Completed on 23-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
15 | Firewall | 192.168.72.1 | Completed on 11-07-2025 | Completed on 23-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
16 | Firewall | 192.168.81.11 | Completed on 11-07-2025 | Completed on 23-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
17 | Firewall | 192.168.84.1 | Completed on 11-07-2025 | Completed on 24-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
18 | Firewall | 192.168.95.10 | Completed on 11-07-2025 | Completed on 24-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
19 | Firewall | 192.168.100.10 | Completed on 11-07-2025 | Completed on 24-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
20 | Firewall | 192.168.105.10 | Completed on 11-07-2025 | Completed on 24-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
21 | Firewall | 192.168.121.22 | Completed on 11-07-2025 | Completed on 24-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
22 | Firewall | 192.168.124.10 | Completed on 11-07-2025 | Completed on 24-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
23 | Firewall | 192.168.145.1 | Completed on 11-07-2025 | Completed on 24-07-2025 | Pratyaksha | Internal Firewall IPs Batch | Report submitted on 04-09-2025
24 | Access point | 12.12.12.2 |  |  | Sukhada |  | On hold due to Accessibility Issue
25 | Access point | 12.12.12.3 |  |  | Sukhada |  | On hold due to Accessibility Issue
26 | Access point | 12.12.12.4 |  |  | Sukhada |  | On hold due to Accessibility Issue
27 | Access point | 12.12.12.5 |  |  | Sukhada |  | On hold due to Accessibility Issue
28 | Access point | 12.12.12.6 |  |  | Sukhada |  | On hold due to Accessibility Issue
29 | Access point | 192.168.41.186 | Completed on 11-07-2025 | Completed on 29-07-2025 | Sukhada | Internal Access Point IPs Batch 1 | Report submitted on 03-09-2025
30 | Access point | 192.168.41.187 | Completed on 11-07-2025 | Completed on 28-07-2025 | Sukhada | Internal Access Point IPs Batch 1 | Report submitted on 03-09-2025
31 | Access point | 192.168.41.188 | Completed on 11-07-2025 | Completed on 28-07-2025 | Sukhada | Internal Access Point IPs Batch 1 | Report submitted on 03-09-2025
32 | Access point | 192.168.41.189 | Completed on 11-07-2025 | Completed on 28-07-2025 | Sukhada | Internal Access Point IPs Batch 1 | Report submitted on 03-09-2025
33 | Access point | 192.168.41.189 |  |  | Sukhada |  | On hold due to Accessibility Issue
34 | Access point | 192.168.41.190 | Completed on 11-07-2025 | Completed on 28-07-2025 | Sukhada | Internal Access Point IPs Batch 1 | Report submitted on 03-09-2025
35 | Access point | 192.168.41.191 | Completed on 11-07-2025 | Completed on 28-07-2025 | Sukhada | Internal Access Point IPs Batch 1 | Report submitted on 03-09-2025
36 | Access point | 192.168.41.192 | Completed on 11-07-2025 | Completed on 28-07-2025 | Sukhada | Internal Access Point IPs Batch 1 | Report submitted on 03-09-2025
37 | Access point | 192.168.41.193 | Completed on 11-07-2025 | Completed on 28-07-2025 | Sukhada | Internal Access Point IPs Batch 1 | Report submitted on 03-09-2025
38 | Access point | 192.168.41.194 | Completed on 11-07-2025 | Completed on 28-07-2025 | Sukhada | Internal Access Point IPs Batch 1 | Report submitted on 03-09-2025
39 | Access point | 192.168.41.195 | Completed on 11-07-2025 | Completed on 28-07-2025 | Sukhada | Internal Access Point IPs Batch 1 | Report submitted on 03-09-2025
40 | Access point | 192.168.41.196 | Completed on 11-07-2025 | Completed on 29-07-2025 | Sukhada | Internal Access Point IPs Batch 1 | Report submitted on 03-09-2025
41 | Access point | 192.168.41.197 | Completed on 11-07-2025 | Completed on 29-07-2025 | Sukhada | Internal Access Point IPs Batch 1 | Report submitted on 03-09-2025
42 | Access point | 192.168.51.206 | Completed on 11-07-2025 | Completed on 29-07-2025 | Sukhada | Internal Access Point IPs Batch 1 | Report submitted on 03-09-2025
43 | Access point | 192.168.51.207 | Completed on 11-07-2025 | Completed on 29-07-2025 | Sukhada | Internal Access Point IPs Batch 1 | Report submitted on 03-09-2025
44 | Access point | 192.168.71.201 | Completed on 11-07-2025 | Completed on 06-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
45 | Access point | 192.168.71.202 | Completed on 11-07-2025 | Completed on 06-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
46 | Access point | 192.168.71.203 | Completed on 11-07-2025 | Completed on 06-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
47 | Access point | 192.168.71.204 | Completed on 11-07-2025 | Completed on 06-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
48 | Access point | 192.168.71.206 | Completed on 11-07-2025 | Completed on 06-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
49 | Access point | 192.168.71.208 | Completed on 11-07-2025 | Completed on 06-08-2026 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
50 | Access point | 192.168.71.209 | Completed on 11-07-2025 | Completed on 07-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
51 | Access point | 192.168.71.220 | Completed on 11-07-2025 | Completed on 07-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
52 | Access point | 192.168.100.52 | Completed on 11-07-2025 | Completed on 07-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
53 | Access point | 192.168.100.56 | Completed on 11-07-2025 | Completed on 07-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
54 | Access point | 192.168.100.57 | Completed on 11-07-2025 | Completed on 07-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
55 | Access point | 192.168.100.63 | Completed on 11-07-2025 | Completed on 07-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
56 | Access point | 192.168.100.100 | Completed on 11-07-2025 | Completed on 07-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
57 | Access point | 192.168.100.107 | Completed on 11-07-2025 | Completed on 07-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
58 | Access point | 192.168.100.118 | Completed on 11-07-2025 | Completed on 11-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
59 | Access point | 192.168.100.119 | Completed on 11-07-2025 | Completed on 11-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
60 | Access point | 192.168.100.129 | Completed on 11-07-2025 | Completed on 11-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
61 | Access point | 192.168.100.136 | Completed on 11-07-2025 | Completed on 11-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
62 | Access point | 192.168.100.138 | Completed on 11-07-2025 | Completed on 11-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
63 | Access point | 192.168.100.156 | Completed on 11-07-2025 | Completed on 11-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
64 | Access point | 192.168.100.190 | Completed on 11-07-2025 | Completed on 11-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
65 | Access point | 192.168.100.204 | Completed on 11-07-2025 | Completed on 11-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
66 | Access point | 192.168.100.218 | Completed on 11-07-2025 | Completed on 11-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
67 | Access point | 192.168.100.233 | Completed on 11-07-2025 | Completed on 12-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
68 | Access point | 192.168.101.242 | Completed on 11-07-2025 | Completed on 12-08-2025 | Pratyaksha | Internal Access Point IPs Batch 2 | Report submitted on 03-09-2025
69 | Switch | 169.253.0.2 |  |  | Sukhada |  | On hold due to Accessibility Issue
70 | Switch | 169.253.0.3 |  |  | Sukhada |  | On hold due to Accessibility Issue
71 | Switch | 169.253.0.6 |  |  | Sukhada |  | On hold due to Accessibility Issue
72 | Switch | 169.254.1.2 |  |  | Sukhada |  | On hold due to Accessibility Issue
73 | Switch | 169.254.1.3 |  |  | Sukhada |  | On hold due to Accessibility Issue
74 | Switch | 172.30.31.2 | Completed on 11-07-2025 | Completed on 21-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
75 | Switch | 172.30.31.3 | Completed on 11-07-2025 | Completed on 21-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
76 | Switch | 172.30.31.4 | Completed on 11-07-2025 | Completed on 21-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
77 | Switch | 172.30.31.5 | Completed on 11-07-2025 | Completed on 21-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
78 | Switch | 192.168.2.2 |  |  | Sukhada |  | On hold due to Accessibility Issue
79 | Switch | 192.168.2.3 |  |  | Sukhada |  | On hold due to Accessibility Issue
80 | Switch | 192.168.2.5 |  |  | Sukhada |  | On hold due to Accessibility Issue
81 | Switch | 192.168.2.6 |  |  | Sukhada |  | On hold due to Accessibility Issue
82 | Switch | 192.168.2.7 |  |  | Sukhada |  | On hold due to Accessibility Issue
83 | Switch | 192.168.2.8 |  |  | Sukhada |  | On hold due to Accessibility Issue
84 | Switch | 192.168.2.9 |  |  | Sukhada |  | On hold due to Accessibility Issue
85 | Switch | 192.168.2.10 |  |  | Sukhada |  | On hold due to Accessibility Issue
86 | Switch | 192.168.2.11 |  |  | Sukhada |  | On hold due to Accessibility Issue
87 | Switch | 192.168.3.4 | Completed on 11-07-2025 | Completed on 25-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
88 | Switch | 192.168.4.3 | Completed on 11-07-2025 | Completed on 25-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
89 | Switch | 192.168.8.3 | Completed on 11-07-2025 | Completed on 25-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
90 | Switch | 192.168.8.4 | Completed on 11-07-2025 | Completed on 25-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
91 | Switch | 192.168.8.5 | Completed on 11-07-2025 | Completed on 25-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
92 | Switch | 192.168.8.23 |  |  | Sukhada |  | On hold due to Accessibility Issue
93 | Switch | 192.168.8.86 | Completed on 11-07-2025 | Completed on 25-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
94 | Switch | 192.168.8.87 | Completed on 11-07-2025 | Completed on 25-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
95 | Switch | 192.168.8.104 | Completed on 11-07-2025 | Completed on 25-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
96 | Switch | 192.168.8.108 | Completed on 11-07-2025 | Completed on 24-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
97 | Switch | 192.168.8.109 | Completed on 11-07-2025 | Completed on 24-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
98 | Switch | 192.168.14.57 | Completed on 11-07-2025 | Completed on 24-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
99 | Switch | 192.168.14.92 | Completed on 11-07-2025 | Completed on 24-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
100 | Switch | 192.168.14.114 | Completed on 11-07-2025 | Completed on 24-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
101 | Switch | 192.168.15.33 | Completed on 11-07-2025 | Completed on 24-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
102 | Switch | 192.168.15.49 | Completed on 11-07-2025 | Completed on 24-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
103 | Switch | 192.168.15.80 | Completed on 11-07-2025 | Completed on 23-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
104 | Switch | 192.168.24.9 | Completed on 11-07-2025 | Completed on 23-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
105 | Switch | 192.168.24.18 | Completed on 11-07-2025 | Completed on 23-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
106 | Switch | 192.168.24.19 | Completed on 11-07-2025 | Completed on 23-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
107 | Switch | 192.168.24.26 | Completed on 11-07-2025 | Completed on 23-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
108 | Switch | 192.168.24.35 | Completed on 11-07-2025 | Completed on 23-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
109 | Switch | 192.168.24.44 | Completed on 11-07-2025 | Completed on 23-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
110 | Switch | 192.168.24.87 | Completed on 11-07-2025 | Completed on 23-07-2025 | Sukhada | Internal Switch IPs Batch 1 | Report submitted on 03-09-2025
111 | Switch | 192.168.25.77 | Completed on 11-07-2025 | Completed on 23-07-2025 | Sukhada | Internal Switch IPs Batch 2 | Reporting in progress
112 | Switch | 192.168.40.5 | Completed on 11-07-2025 | Completed on 22-07-2025 | Sukhada | Internal Switch IPs Batch 2 | Reporting in progress
113 | Switch | 192.168.41.124 | Completed on 11-07-2025 | Completed on 22-07-2025 | Sukhada | Internal Switch IPs Batch 2 | Reporting in progress
114 | Switch | 192.168.41.125 | Completed on 11-07-2025 | Completed on 22-07-2025 | Sukhada | Internal Switch IPs Batch 2 | Reporting in progress
115 | Switch | 192.168.41.126 | Completed on 11-07-2025 | Completed on 22-07-2025 | Sukhada | Internal Switch IPs Batch 2 | Reporting in progress
116 | Switch | 192.168.41.127 | Completed on 11-07-2025 | Completed on 22-07-2025 | Sukhada | Internal Switch IPs Batch 2 | Reporting in progress
117 | Switch | 192.168.41.128 | Completed on 11-07-2025 | Completed on 22-07-2025 | Sukhada | Internal Switch IPs Batch 2 | Reporting in progress
118 | Switch | 192.168.41.129 | Completed on 11-07-2025 | Completed on 22-07-2025 | Sukhada | Internal Switch IPs Batch 2 | Reporting in progress
119 | Switch | 192.168.41.130 | Completed on 11-07-2025 | Completed on 17-07-2025 | Sukhada | Internal Switch IPs Batch 2 | Reporting in progress
120 | Switch | 192.168.41.131 | Completed on 11-07-2025 | Completed on 17-07-2025 | Sukhada | Internal Switch IPs Batch 2 | Reporting in progress
121 | Switch | 192.168.41.183 | Completed on 11-07-2025 | Completed on 17-07-2025 | Sukhada | Internal Switch IPs Batch 2 | Reporting in progress
122 | Switch | 192.168.51.122 | Completed on 11-07-2025 | Completed on 19-08-2025 | Pratyaksha | Internal Switch IPs Batch 2 | Reporting in progress
123 | Switch | 192.168.51.123 | Completed on 11-07-2025 | Completed on 19-08-2025 | Pratyaksha | Internal Switch IPs Batch 2 | Reporting in progress
124 | Switch | 192.168.51.124 | Completed on 11-07-2025 | Completed on 20-08-2025 | Pratyaksha | Internal Switch IPs Batch 2 | Reporting in progress
125 | Switch | 192.168.51.125 | Completed on 11-07-2025 | Completed on 20-08-2025 | Pratyaksha | Internal Switch IPs Batch 2 | Reporting in progress
126 | Switch | 192.168.56.8 | Completed on 11-07-2025 | Completed on 20-08-2025 | Pratyaksha | Internal Switch IPs Batch 2 | Reporting in progress
127 | Switch | 192.168.56.23 | Completed on 11-07-2025 | Completed on 20-08-2025 | Pratyaksha | Internal Switch IPs Batch 2 | Reporting in progress
128 | Switch | 192.168.56.30 | Completed on 11-07-2025 | Completed on 22-08-2025 | Pratyaksha | Internal Switch IPs Batch 2 | Reporting in progress
129 | Switch | 192.168.56.221 | Completed on 11-07-2025 | Completed on 22-08-2025 | Pratyaksha | Internal Switch IPs Batch 2 | Reporting in progress
130 | Switch | 192.168.56.222 | Completed on 11-07-2025 | Completed on 25-08-2025 | Pratyaksha | Internal Switch IPs Batch 2 | Reporting in progress
131 | Switch | 192.168.56.223 | Completed on 11-07-2025 | Completed on 25-08-2025 | Pratyaksha | Internal Switch IPs Batch 2 | Reporting in progress
132 | Switch | 192.168.56.224 | Completed on 11-07-2025 | Completed on 25-08-2025 | Pratyaksha | Internal Switch IPs Batch 2 | Reporting in progress
133 | Switch | 192.168.56.226 | Completed on 11-07-2025 | Completed on 26-08-2025 | Pratyaksha | Internal Switch IPs Batch 2 | Reporting in progress
134 | Switch | 192.168.56.227 | Completed on 11-07-2025 | Completed on 26-08-2025 | Pratyaksha | Internal Switch IPs Batch 2 | Reporting in progress
135 | Switch | 192.168.56.228 | Completed on 11-07-2025 | Completed on 26-08-2025 | Pratyaksha | Internal Switch IPs Batch 2 | Reporting in progress
136 | Switch | 192.168.56.229 | Completed on 11-07-2025 | Completed on 28-08-2025 | Pratyaksha | Internal Switch IPs Batch 2 | Reporting in progress
137 | Switch | 192.168.56.230 | Completed on 11-07-2025 |  | Pratyaksha
138 | Switch | 192.168.56.231 | Completed on 11-07-2025 | Completed on 28-08-2025 | Pratyaksha
139 | Switch | 192.168.56.232 | Completed on 11-07-2025 |  | Pratyaksha
140 | Switch | 192.168.56.233 | Completed on 11-07-2025 | Completed on 29-08-2025 | Pratyaksha
141 | Switch | 192.168.56.234 | Completed on 11-07-2025 | Completed on 29-08-2025 | Pratyaksha
142 | Switch | 192.168.56.235 | Completed on 11-07-2025 | Completed on 02-09-2025 | Pratyaksha
143 | Switch | 192.168.56.236 | Completed on 11-07-2025 |  | Pratyaksha
144 | Switch | 192.168.56.237 | Completed on 11-07-2025 | Completed on 02-09-2025 | Pratyaksha
145 | Switch | 192.168.56.238 | Completed on 11-07-2025 | Completed on 02-09-2025 | Pratyaksha
146 | Switch | 192.168.57.155 | Completed on 11-07-2025 | Completed on 02-09-2025 | Pratyaksha
147 | Switch | 192.168.71.53 | Completed on 11-07-2025 | Completed on 03-09-2025 | Pratyaksha
148 | Switch | 192.168.71.250 | Completed on 11-07-2025 | Completed on 03-09-2025 | Pratyaksha
149 | Switch | 192.168.81.7 | Completed on 11-07-2025 | Completed on 03-09-2025 | Pratyaksha
150 | Switch | 192.168.81.8 | Completed on 11-07-2025 | Completed on 03-09-2025 | Pratyaksha
151 | Switch | 192.168.81.9 | Completed on 11-07-2025 | Completed on 05-09-2025 | Pratyaksha
152 | Switch | 192.168.81.12 | Completed on 11-07-2025 | Completed on 05-09-2025 | Pratyaksha
153 | Switch | 192.168.81.13 | Completed on 11-07-2025 | Completed on 05-09-2025 | Pratyaksha
154 | Switch | 192.168.81.120 | Completed on 11-07-2025 | Completed on 05-09-2025 | Pratyaksha
155 | Switch | 192.168.81.121 | Completed on 11-07-2025 | Completed on 09-09-2025 | Pratyaksha
156 | Switch | 192.168.81.131 | Completed on 11-07-2025 | Completed on 09-09-2025 | Pratyaksha
157 | Switch | 192.168.81.214 | Completed on 11-07-2025 | Completed on 09-09-2025 | Pratyaksha
158 | Switch | 192.168.81.215 | Completed on 11-07-2025 | Completed on 09-09-2025 | Pratyaksha
159 | Switch | 192.168.81.223 | Completed on 11-07-2025 | Completed on 09-09-2025 | Pratyaksha
160 | Switch | 192.168.81.224 | Completed on 11-07-2025 | Completed on 11-09-2025 | Pratyaksha
161 | Switch | 192.168.81.225 | Completed on 11-07-2025 | Completed on 11-09-2025 | Pratyaksha
162 | Switch | 192.168.81.235 | Completed on 11-07-2025 | Completed on 11-09-2025 | Pratyaksha
163 | Switch | 192.168.81.247 | Completed on 11-07-2025 | Completed on 11-09-2025 | Pratyaksha
164 | Switch | 192.168.85.24 | Completed on 11-07-2025 | Completed on 12-09-2025 | Pratyaksha
165 | Switch | 192.168.85.27 | Completed on 11-07-2025 | Completed on 12-09-2025 | Pratyaksha
166 | Switch | 192.168.85.33 | Completed on 11-07-2025 | Completed on 12-09-2025 | Pratyaksha
167 | Switch | 192.168.85.42 | Completed on 11-07-2025 | Completed on 12-09-2025 | Pratyaksha
168 | Switch | 192.168.85.91 | Completed on 11-07-2025 | Completed on 12-09-2025 | Pratyaksha
169 | Switch | 192.168.85.93 | Completed on 11-07-2025 |  | Pratyaksha
170 | Switch | 192.168.100.11 | Completed on 11-07-2025 |  | Pratyaksha
171 | Switch | 192.168.100.18 | Completed on 11-07-2025 |  | Pratyaksha
172 | Switch | 192.168.100.19 | Completed on 11-07-2025 |  | Pratyaksha
173 | Switch | 192.168.101.11 | Completed on 11-07-2025 |  | Pratyaksha
174 | Switch | 192.168.101.239 | Completed on 11-07-2025 |  | Pratyaksha
175 | WLC | 192.168.8.100 | Completed on 11-07-2025 | Completed on 17-07-2025 | Pratyaksha | Internal WLC IPs Batch | Report submitted on 11-08-2025
176 | WLC | 192.168.15.253 | Completed on 11-07-2025 | Completed on 18-07-2025 | Pratyaksha | Internal WLC IPs Batch | Report submitted on 11-08-2025
177 | WLC | 192.168.41.200 | Completed on 11-07-2025 | Completed on 18-07-2025 | Pratyaksha | Internal WLC IPs Batch | Report submitted on 11-08-2025
178 | WLC | 192.168.56.50 | Completed on 11-07-2025 | Completed on 21-07-2025 | Pratyaksha | Internal WLC IPs Batch | Report submitted on 11-08-2025
179 | WLC | 192.168.71.200 | Completed on 11-07-2025 | Completed on 21-07-2025 | Pratyaksha | Internal WLC IPs Batch | Report submitted on 11-08-2025

## BAS 1st Activity Tracker
Action Item | Detailed Task Description | Responsibility | Tentative Timeline | Current Status & Notes
Sharing of Pre-requisites | Pre-requisite documents and setup information shared with EPL for initial setup | Aquila I Team | 2025-04-23 | Completed
Tenant Setup | Fresh tenant successfully configured for BAS deployment | Aquila I Team | 2025-04-23 | Completed
BAS Agent Whitelisting | Whitelisting of the BAS agent on EPL’s security infrastructure | EPL Team | 2025-07-17 | Installed agents on 11 systems
Identification of Target Systems | Identification of 10 critical systems for BAS agent installation | EPL Team | 2025-07-17 | EPL team identified and installed agents on 11 systems
Installation of BAS Agent | Installation of BAS agent on the selected 10 systems | EPL Team | 2025-07-17 | Done
Initiation of Execution Activities | Start executing BAS activities and monitoring across identified systems | Aquila I & EPL Team | 2025-07-22 | Aquila I Team executed the following attack vectors on one agent (INMUMNB724), which had admin access: -Endpoint -Web Gateway -Data Exfiltration -WAF (No WAF performed as EPL team does not have a WAF environment)
Reporting on BAS Execution | Compilation of findings and detailed activity reports based on BAS monitoring | Aquila I Team | 2025-08-01 | Pending
Executive Summary & Recommendations | Share executive insights, key risk indicators, and recommendations from BAS analysis | Aquila I Team | 2025-08-01 | Pending

## ASM
Action Item | Detailed Task Description | Responsibility | Tentative Timeline | Current Status & Remarks
1. Sharing of Pre-requisites | Initial pre-requisite documents and setup guidelines shared with EPL to initiate onboarding | Aquila I Team | 2025-04-23 | Completed
2. Tenant Setup | Setup of a fresh ASM tenant environment for EPL’s attack surface monitoring | Aquila I Team | 2025-04-23 | Completed
3. Sharing of Domain & Public IPs | EPL to share 1 primary domain and 4 public IP addresses to initiate monitoring | EPL Team | 2025-04-23 | Completed on 30-May-2025
4. Monitoring Initiation | Aquila I to initiate continuous monitoring for shared domain and IPs | Aquila I Team | 2025-04-25 | Partially Completed – Monitoring started for the shared domain and IPs related to the domain on 30-May-2025. Awaiting confirmation on monitoring of the public IPs.
5. Reporting | Weekly and monthly reports to be generated and shared with EPL covering identified vulnerabilities | Aquila I Team | 2025-04-25 | Completed – Automated reporting configured
6. Alerts Enablement | Real-time alert mechanism to be activated for any critical vulnerabilities or asset exposures detected during monitoring | Aquila I Team | 2025-04-25 | Completed – Alerting successfully enabled and active

## ASM Vulnerability Tracker (EPL)
Category | Number of Vulnerabilities Identified | Number of Vulnerabilities Mitigated | Number of Vulnerabilities Pending | Remarks/Notes
Port Vulnerability | 358
Web Vulnerability | 8
IP Vulnerability | 303

## Applicaiton Owner (hidden)
Web | Owners | mail | Follow-up | Follow-up | Follow-up
WebApp-External URL | Pratap Bhalerao | sent
WebApp-Labour Works | Milind Ghate | sent | sent | sent | sent
WebApp-BPM | Santosh Gosavi | sent | sent | sent
WebApp-E-act | E-act team | sent | sent | sent | sent
WebApp-Zing HR | Kavya Verma, Stefi Farel | sent | sent | sent
WebApp-E-prism | Anandita Raha, Jaya Mohan | sent | sent | sent | sent
WebApp-Internal cognos | Rohit Mandavkar | sent | sent | sent | sent
WebApp-Internal Entegra | Santosh Gosavi | sent | sent | sent | sent
WebApp-SAP-Authorization | Rajesh Shrivastav | sent | sent | sent
WebAppE-sop | Omkar Gangurde | sent | sent | sent
Server-External Ips | Pratap Bhalerao | sent
Network Devices | Pratap Bhalerao | sent

## RoadBlocks
Sr.No | Issues | Date | Issue Status | Remark | Status
1 | Second Internal EPL System | 2025-05-22 | Second system is not recieved due to which both the tester cannot perform parellel testing on the internal URL | Received second system access on 06/05/2025 | Closed
2 | Duplicate URL &Thirdparty URL | 2025-06-20 | #Two web applications are out of scope, requesting to jitendra the replacement of the removed applications from scope. #As confirmed on trail mail that we do not have to perform the testing on EPL Dashboard as it is hosted on PowerBi which is third party application and you don’t have permission to fix the issues. #The Safety Portal Web application as it is duplicate of ENTGRA Web application. | Confirmed replacement of 2 URL on 06/30/2025 | Closed
3 | Internal Network Device IPs Accessibility issue | 2025-07-24 | #19 IPs are not accessible from VAPT-TEMP internal system, but they are accessible from VAPT2 internal system. #23 IPs are also not accessible from both VAPT-TEMP and VAPT2 internal systems. We suspect them to be down. | Confirmation pending from EPL Team. | Open
4 | Internal Server IPs Accessibility issue | 2025-08-28 | #49 IPs are also not accessible from both VAPT-TEMP and VAPT2 internal systems. We suspect them to be down. | Confirmation pending from EPL Team. | Open