## Slide 1
Weekly Status Meeting Update
VAPT, BAS and ASM Project
25 Sep 2025

## Slide 2
VAPT
Bug Fixes
Functional Excellence
Simplification
And
Automation
Analytics
Efficiency Achieved
Progress Last week-
Web Application
14 Web Application Initial Reports Submitted.
Server
Scope Count – 300, Received Count from EPL – 342. Completed VA – 295 and Completed PT - 89
Network Devices
Scope Count – 200, Received Count from EPL – 179. Completed VA – 157 and Completed PT - 148
Plan for This week-
Key Risks / Points to be highlighted-
Key Achievement-
Sr.No | Issues | Date | Issue Status | Remark
1 | Internal Network Device IPs Accessibility issue | 24-07-2025 | #19 IPs are not accessible from VAPT-TEMP internal system, but they are accessible from VAPT2 internal system. #23 IPs are also not accessible from both VAPT-TEMP and VAPT2 internal systems. We suspect them to be down. | Confirmation pending from EPL Team.
2 | Internal Server IPs Accessibility issue | 28-08-2025 | #49 IPs are also not accessible from both VAPT-TEMP and VAPT2 internal systems. We suspect them to be down. | Confirmation pending from EPL Team.
1. To complete testing for 30 Server Ips.
2. To complete Reporting for Switch Ips batch 2 Report and send it. Need update for IP accessibility issue to start testing of remaining Ips.
3. To complete testing of 4 Internal Web Applications and to share reports for 4 Internal Web Applications.

## Slide 3
BAS
Bug Fixes
Functional Excellence
Simplification
And
Automation
Analytics
Efficiency Achieved
Progress Last week-
2nd BAS Agent - Tried to run the playbook on the existing 1 agent without NT Authority, but it is getting blocked with an "Access Denied" message.
Plan for This week-
The EPL team has informed us that they will check the regarding the access issue from their end and get back to us.
Key Risks / Points to be highlighted-
Awaiting response from the EPL team for installation of other agents with NT Authority/Admin access.
Key Achievement-

## Slide 4
ASM
Bug Fixes
Functional Excellence
Simplification
And
Automation
Analytics
Efficiency Achieved
Progress Last week-
Daily scanning is ongoing.
Weekly and monthly auto reports are generated and sent.
Plan for This week-
Continuous monitoring of the shared assets is in progress.
Mitigation of detected vulnerabilities is awaited from the EPL team.
Key Risks / Points to be highlighted-
Awaiting update from the EPL team on the closure of identified vulnerabilities.
Key Achievement-